## Adani Projects
Project ID | Project Name | Parent | Project Owner (Subsidiary) | Sector | State | City | Project Status | Project Type | Construction Start Date | Expected Commissioning Date | Scope
ADN-UTL-001 | Khavda Renewable Energy Park (30 GW) | Adani Group | Adani Green Energy Ltd (AGEL) | Utilities | Gujarat | Khavda, Kutch | Ongoing | Greenfield | Dec 2020 | 2030 (Phased; >9.4 GW operational by FY26) | 30 GW solar + wind RE park. World's largest single-site RE park. EPC: SWREL, Bondada Engineering, KPI Green. ₹1,50,000 Cr committed.
ADN-UTL-002 | Khavda BESS Deployment (1,376 MWh) | Adani Group | Adani Green Energy Ltd (AGEL) | Utilities | Gujarat | Khavda, Kutch | Completed | Capacity Addition | 2025 | Apr 2026 | 1,376 MWh BESS deployed at Khavda RE Park to support grid stability. EPC: Adani Green Energy.
ADN-UTL-003 | Panaura Pumped Hydro Storage (1,250 MW) | Adani Group | Adani Green Energy Ltd (AGEL) / Adani Saur Urja | Utilities | Uttar Pradesh | Sonbhadra District | Ongoing | Greenfield | 2025 | 2031 (~6 years from UPPCL award) | 1,250 MW pumped storage hydro awarded by UPPCL. 40-year commitment, 6-year execution timeline. Pre-construction/planning stage.
ADN-UTL-004 | Gandikota Pumped Hydro (1,800 MW) | Adani Group | Adani Green Energy Ltd (AGEL) | Utilities | Andhra Pradesh | YSR Kadapa District | Ongoing | Greenfield | 2025 (Equipment ordered) | ~2030 (Early 2030s estimated) | 1,800 MW pumped hydro. ANDRITZ awarded electromechanical package Q2 2025. Civil works not yet started.
ADN-UTL-005 | Mahan Super Thermal Power Expansion (2×800 MW) | Adani Group | Adani Power Ltd / Mahan Energen Ltd | Utilities | Madhya Pradesh | Bandhaura, Singrauli District | Ongoing | Brownfield Expansion | 2025 | FY2029-30 (Estimated) | 1,600 MW ultra-supercritical brownfield expansion at existing 1,200 MW Mahan plant. Part of ₹1,20,000 Cr capex plan.
ADN-UTL-006 | Pirpainti Thermal Power Plant (3×800 MW) | Adani Group | Adani Power Ltd | Utilities | Bihar | Pirpainti, Bhagalpur District | Ongoing | Greenfield | Mar 2026 (LoA Award) | First unit ~48 months; full plant ~60 months from appointed date | 2,400 MW greenfield USCTPP for Bihar DISCOMs. EPC: BTL EPC Ltd. PSA signed 13-Sep-2025. Investment ~₹590 Cr (BTL package). Total ~₹26,482 Cr project.
ADN-OG-001 | Pan-India CNG & PNG Infrastructure Expansion | Adani Group | Adani Total Gas Ltd (ATGL) | Oil & Gas | Multiple (13 States) | Multiple Cities / Geographical Areas | Ongoing | Capacity Addition | Dec 2024 (7-year plan announced) | 2031-32 (Rolling commissioning) | Expansion of CNG stations and PNG pipeline networks across 50+ GAs in 13 states. Investment ₹16,000 Cr over 7 years. 600+ CNG stations already operational.
ADN-MIN-001 | Suliyari Coal Mine Expansion (7 MTPA) | Adani Group | Adani Enterprises Ltd (MDO) | Mining | Madhya Pradesh | Singrauli District | Ongoing | Expansion | 2021 | Ongoing Extraction | 7 MTPA captive coal mine under Adani as MDO. Project value ₹386.20 Cr. Operational and in extraction phase.
ADN-MIN-002 | Badam Coal Mine (MDO) | Adani Group | Adani Enterprises Ltd (MDO) | Mining | Jharkhand | Hazaribagh District | Completed | Greenfield | 2024 | Feb 2025 | Coal mine developed by Adani Enterprises as MDO. Commissioned Feb 2025.
ADN-DC-001 | Navi Mumbai Hyperscale Data Centre (1 GW) | Adani Group | Adani Enterprises Ltd / AdaniConneX JV | Data Centres | Maharashtra | Navi Mumbai | Upcoming | Greenfield | Not Disclosed | Dec 2026 (Phase 1) | 1 GW hyperscale DC infrastructure. MoU signed Jan 2024 (WEF Davos) with Maharashtra Govt. Investment ₹50,000 Cr over 10 years.
ADN-DC-002 | Pune Data Centre (250 MW) | Adani Group | Adani Enterprises Ltd / AdaniConneX JV | Data Centres | Maharashtra | Pune | Ongoing | Greenfield | Not Disclosed | H2 2025 (Phase 1) | 250 MW data centre campus in Pune. Part of Maharashtra 1 GW DC program under MoU Jan 2024.
ADN-DC-003 | Hyderabad Data Centre (600 MW) | Adani Group | Adani Enterprises Ltd / AdaniConneX JV | Data Centres | Telangana | Hyderabad | Ongoing | Greenfield | Not Disclosed | Oct 2024 (Phase 1) | 600 MW hyperscale data centre. Phase 1 commissioned Oct 2024. AdaniConneX JV development.
ADN-DC-004 | Visakhapatnam AI Data Centre Campus | Adani Group | Adani Enterprises Ltd / AdaniConneX JV | Data Centres | Andhra Pradesh | Visakhapatnam | Upcoming | Greenfield | 2026 (Planning & design) | 2030 (Phased build-out starts 2026) | India's largest AI-oriented DC campus. Adani-Google partnership announced Oct 2025. Part of ~US$15 Bn (~₹1,25,000 Cr) multi-year India investment.