## NTPC Projects
Project ID | Project Name | Parent | Project Owner (Subsidiary) | Sector | State | City | Project Status | Project Type | Construction Start Date | Expected Commissioning Date | Scope
NTP-THM-001 | Telangana Super Thermal Power Project Stage-I (2×800 MW = 1,600 MW) | NTPC Limited | NTPC Ltd | Thermal | Telangana | Peddapalli District (near Ramagundam) | Completed | Greenfield | Not Disclosed (PPA signed 18-01-2016; civil works mid-2010s) | Unit-1: 05-09-2023 ¦ Unit-2: 04-03-2024 (dedicated by PM) | 1,600 MW ultra-supercritical (USC) coal plant. Efficiency ~42%, reduced CO₂/kWh. 85% power allocated to Telangana state. Technology: USC boiler-turbine-generator.
NTP-THM-002 | Lara Super Thermal Power Project Stage-II (2×800 MW = 1,600 MW) | NTPC Limited | NTPC Ltd | Thermal | Chhattisgarh | Raigarh District (near Lara) | Ongoing | Brownfield Expansion | 30-08-2023 (NTPC board investment approval + BHEL EPC order) | Unit-1: ~2028 ¦ Unit-2: ~2029 (48/52 months from contract zero date) | 1,600 MW USC/USC+ expansion on Stage-I land. Full-scope EPC by BHEL (BTG + BoP). Designed for biomass co-firing and advanced emission controls. Investment: ₹15,529.99 Cr. Coal: Talaipalli block.
NTP-THM-003 | Talcher Thermal Power Project Stage-III (2×660 MW = 1,320 MW) | NTPC Limited | NTPC Ltd (Talcher Thermal) | Thermal | Odisha | Angul District (Talcher) | Ongoing | Brownfield Expansion | 27-09-2022 (BHEL EPC order for 2×660 MW Stage-III) | Unit-1: Mar 2027 ¦ Unit-2: Not Disclosed (expected shortly after Unit-1) | 1,320 MW supercritical coal expansion replacing old units. Full-scope EPC by BHEL (BTG + BoP). Board-approved capex: ~₹9,785 Cr.
NTP-THM-004 | North Karanpura Super Thermal Power Project (3×660 MW = 1,980 MW) | NTPC Limited | NTPC Ltd | Thermal | Jharkhand | Chatra District (North Karanpura) | Completed | Greenfield | Not Disclosed (construction since early 2010s) | Unit-1: 01-03-2023 ¦ Unit-2: 04-03-2024 ¦ Unit-3: Jun 2025 (trial ops 11-06-2025) | 1,980 MW supercritical coal plant. India's first large air-cooled condenser (ACC) — reduces water use to 1/3 of conventional plants. Pithead coal supply. Supports eastern regional grid.
NTP-SOL-001 | Khavda-I Solar PV Project (1,255 MW) | NTPC Limited | NTPC Renewable Energy Ltd (subsidiary of NTPC Green Energy Ltd) | Solar | Gujarat | Khavda, Kutch District | Ongoing | Greenfield | Not Disclosed (first part COD 05-06-2025 as proxy) | Phased CODs through FY26: 142.2 MW (28-06-2025), +32.8 MW, +49.1 MW, +75.5 MW, +95.75 MW, +69 MW etc. Full 1,255 MW by FY26 | 1,255 MW ground-mounted solar PV under CPSU Phase-II Tranche-III (ISTS-connected). Developed by NTPC REL for self-use. Part of NGEL's 60 GW by 2032 target.
NTP-SOL-002 | Nokh Solar PV Project (245 MW) | NTPC Limited | NTPC Renewable Energy Ltd / NTPC Green Energy Ltd | Solar | Rajasthan | Nokh, Jaisalmer District | Ongoing | Greenfield | Not Disclosed (tendered under CPSU scheme; first COD 2025) | First 78 MW commissioned 2025; remaining 167 MW by FY26 (exact unit-wise dates not disclosed) | 245 MW solar PV under CPSU scheme. Feeds NTPC internal and ISTS demand. Contributes to NGEL's 32+ GW RE portfolio.
NTP-SOL-003 | Chhattargarh Solar PV Project (150 MW) | NTPC Limited | NTPC Renewable Energy Ltd (NTPC REL) | Solar | Rajasthan | Chhattargarh, Bikaner District | Completed | Greenfield | Not Disclosed (under execution prior to FY24) | 70 MW: 21-02-2024 ¦ Full 150 MW: 29-03-2024 | 150 MW grid-connected solar PV. First operational project of NTPC REL. Part of NTPC REL's ~3.5 GW RE under execution as of 31-03-2024.
NTP-SOL-004 | Kadapa Solar PV Project (250 MW) | NTPC Limited | ONGC NTPC Green Pvt Ltd (JV of NTPC Green Energy Ltd & ONGC) | Solar | Andhra Pradesh | Kadapa District | Completed | Greenfield | Not Disclosed (developed by Ayana Kadapa Renewable Power Pvt Ltd) | 158.4 MW: Feb 2026 ¦ Full 250 MW: 08-03-2026 | 250 MW solar PV. Developed by Ayana Kadapa Renewable Power (ONGC-NTPC Green JV subsidiary). 25-year PPA with SECI at ₹2.71/kWh. Contributes ~9.3 GW NGEL installed RE capacity.
NTP-HYD-001 | Tehri Pumped Storage Plant (4×250 MW = 1,000 MW Variable-Speed PSP) | NTPC Limited | THDC India Ltd (NTPC subsidiary) | Hydro | Uttarakhand | Tehri Garhwal (Tehri & Koteshwar reservoirs, Bhagirathi River) | Completed | Brownfield Expansion | Not Disclosed (PSP construction ongoing since 2011; final commissioning phase 2024-26) | Unit-1: 07-06-2025 ¦ Unit-2: 10-07-2025 ¦ Unit-3: Dec 2025 ¦ Unit-4: Jan 2026 | India's first variable-speed PSP (4×250 MW). Uses Tehri HPP as upper and Koteshwar HEP as lower reservoir. Provides flexible peaking power and grid balancing. Project cost: ~₹8,339 Cr.
NTP-HYD-002 | Vishnugad Pipalkoti Hydro Electric Project – VPHEP (4×111 MW = 444 MW) | NTPC Limited | THDC India Ltd | Hydro | Uttarakhand | Chamoli District (Alaknanda River) | Ongoing | Greenfield | 2011 (project approval and construction start; multiple extensions since) | Not Disclosed (earlier target Oct 2024 slipped; updated COD not publicly stated as of early 2026) | 444 MW run-of-river HEP. 65 m diversion dam, 13.4 km headrace tunnel, underground powerhouse. Generates ~1,665 GWh/year for northern grid. ~40-50% physical progress. Partly financed by World Bank.
NTP-NUC-001 | Mahi Banswara Rajasthan Atomic Power Project – MBRAPP (4×700 MW = 2,800 MW PHWR) | NTPC Limited | ASHVINI – Anushakti Vidhyut Nigam Ltd (JV: NPCIL 51% + NTPC 49%) | Nuclear | Rajasthan | Banswara District | Upcoming | Greenfield | 25-09-2025 (Foundation stone for Units 1&2 laid by PM) | Not Disclosed (typical fleet-mode PHWR: ~6-7 years per twin-unit block; no binding COD published) | 4×700 MW indigenous IPHWR-700 PHWR. Two phases: Units 1&2 and Units 3&4. Estimated cost: ~₹42,000 Cr. First nuclear project by two CPSEs via JV. India's fleet-mode nuclear expansion.
NTP-NUC-002 | Chutka Madhya Pradesh Atomic Power Project (2×700 MW PHWR) | NTPC Limited | ASHVINI – Anushakti Vidhyut Nigam Ltd (JV: NPCIL 51% + NTPC 49%) | Nuclear | Madhya Pradesh | Mandla District (Chutka Village, Narayanganj Tehsil) | Upcoming | Greenfield | Not Disclosed (pre-project activities: land acquisition, clearances, surveys since 2009; no concrete-start date declared) | Not Disclosed (Global Energy Monitor lists ~2031; no binding GoI/NPCIL COD published) | 2×700 MW IPHWR-700 indigenous PHWR. Estimated cost: ~₹25,000 Cr. Part of fleet-mode nuclear expansion under ASHVINI JV alongside Mahi Banswara.
NTP-BES-001 | Standalone BESS at Gadarwara & Solapur (250 MW / 500 MWh) | NTPC Limited | NTPC Ltd (RE Division) | Utilities | Madhya Pradesh & Maharashtra | Gadarwara (Narsinghpur, MP) & Solapur (MH) | Upcoming | Greenfield | 13-06-2024 (IFB issued: 150 MW/300 MWh Gadarwara + 100 MW/200 MWh Solapur) | Not Disclosed (commissioning post-tender award; ~12-year EPC + O&M term) | 250 MW / 500 MWh grid-connected standalone BESS at two NTPC sites. Two 2-hour daily cycles, ≥80% round-trip efficiency. Supports Gadarwara solar plant (MP) and Solapur coal station (MH). Includes design, supply, grid integration, and long-term O&M.
NTP-BES-002 | NTPC 4.7 GWh Battery Energy Storage System Program (Multi-Site) | NTPC Limited | NTPC Ltd / NTPC Renewable Energy Ltd | Utilities | Multiple States | Mouda, Kudgi, Ramagundam, Solapur, Barh, Nabinagar, Simhadri, Bikaner (Multiple Sites) | Upcoming | Greenfield | 2025-26 (Multiple BESS tenders issued; board investment approval Apr 2026; 2.334 GWh Lot-I awarded Mar 2026) | Not Disclosed (staggered commissioning post-award at each site; 11-year O&M term) | Portfolio of utility-scale BESS totalling 4.7 GWh (~₹5,822 Cr capex). Winners include GR Infraprojects. Sites: Mouda, Kudgi, Ramagundam, Solapur, Barh, Nabinagar, Simhadri + 250 MW/1,000 MWh at Bikaner RE. Firms RE output and provides peak/ancillary grid services.