## ONGC Projects
ONGC Group — Major Projects Tracker (2024–2026)
ID | Project Name | Conglomerate | Sector | Scope / Description | State | City / Location | Contractor / EPC | Start Date | Commissioning Date | Project Value | Status | Subsidiary
ONG-001 | KG-DWN-98/2 Cluster-II Deepwater Development | ONGC | Oil & Gas | Deepwater gas/condensate development; FPSO Armada Sterling V; Subsea SPS+SURF EPC; First oil Jan 2024; production ramp-up ongoing | Offshore Andhra Pradesh | ~35 km off Kakinada, KG Basin | Consortium: Baker Hughes + McDermott + L&T Hydrocarbon (LTHE) | Oct 2018 (EPC Award) | Jan 2024 (First Oil); Full by Q1 FY27 | ~₹41,000 Cr (USD 5 Billion) | 🟡 Under Production / Final Commissioning | ONGC (Direct)
ONG-002 | Mumbai High North Redevelopment Phase-IV (MHN RD-IV) | ONGC | Oil & Gas | Offshore redevelopment of Mumbai High North field; platform upgrade and subsea works; dedicated by PM Mar 2024; cost overrun ~23% | Offshore Maharashtra | Arabian Sea, ~160 km west of Mumbai | Multiple offshore/drilling contractors (Not named publicly) | Apr 2019 (Sanction) | Feb 2025 (Formal Completion) | ₹3,976.67 Cr (revised; orig. ₹3,228.80 Cr) | 🟢 Completed | ONGC (Direct)
ONG-003 | Daman Upside Development Project (DUDP) | ONGC | Oil & Gas | Western offshore gas development; platform B-12-24P; gas flowing to Hazira plant from Mar 29, 2026; completed in <2 years from award | Western Offshore, Arabian Sea | ~180 km NW of Mumbai; ~80 km south of Pipavav | L&T Energy (EPCIC) | Late 2024 (EPC Award) | Mar 29, 2026 (Gas Monetisation Started) | ~₹8,300 Cr (USD 1 Billion) | 🟢 Commissioned (2026) | ONGC (Direct)
ONG-004 | Subsea Pipeline Replacements (PRP-VIII & PRP-9) | ONGC | Oil & Gas | Replacement of aging subsea pipelines across Mumbai High, Neelam and Heera fields; PRP-9 EPC to Lamprell | Western Offshore | Mumbai High, Neelam, Heera fields | Lamprell (PRP-9); Other contractors (PRP-VIII) | 2024–25 | 2026–2027 | ₹13,000 Cr+ | 🟡 Under Execution | ONGC (Direct)
ONG-005 | Jharia Coal Bed Methane (CBM) Project | ONGC | Oil & Gas | CBM gas extraction from Jharia coalfields; JV with Coal India; gas to be monetised from coal seams | Jharkhand | Jharia | TBD (JV with Coal India) | 2024 | 2027 | ₹3,000 Cr | 🟡 Under Implementation | ONGC (Direct)
ONG-006 | DSF-II Integrated Development (4 Areas) | ONGC | Oil & Gas | Discovered Small Field-II integrated development across 4 offshore continental shelf areas; Board approved Aug 2024 | Offshore (Multiple) | Various Continental Shelf sites | TBD | Aug 2024 (Board Approval) | Apr 2027 | ₹6,000 Cr | 🟡 Ongoing / Construction | ONGC (Direct)
ONG-007 | Andaman Basin Stratigraphic Well (AND-P-1) | ONGC | Oil & Gas | Ultra-deepwater exploratory well 267 nautical miles from Andaman Islands; technical SME support from BP; spudded Jan 27, 2026 | Andaman Basin (Offshore) | 267 nm from Andaman Islands | BP (Technical SME) | Jan 27, 2026 (Spud) | TBD (Exploration) | Part of ₹12,000 Cr exploration budget | 🟡 Active Drilling | ONGC (Direct)
ONG-008 | HPCL Visakh Refinery Modernisation Project (VRMP) + RUF | ONGC | PCR | Expanded refinery from 8.33 to 15 MMTPA; added BS-VI capability; LC-Max residue hydrocracking unit (3.55 MMTPA); RUF commissioned early 2026 | Andhra Pradesh | Visakhapatnam (Visakh Refinery, Malkapuram) | EIL (PMC); Lummus Technology (LC-Max license) | Jul 2016 (Board Approval) | Early 2026 (RUF commissioned; 15 MMTPA refinery complete) | ₹30,609 Cr (revised; orig. ₹26,264 Cr) | 🟢 Completed (2026) | HPCL (ONGC subsidiary)
ONG-009 | MRPL Iso-Butyl Benzene (IBB) Demo Plant | ONGC | PCR | Demonstration-scale IBB production plant at MRPL Mangalore refinery; in-house development | Karnataka | Mangalore Refinery (MRPL site) | In-house / EPC | 2023 | Nov 2025 | Not Disclosed | 🟢 Completed | MRPL (ONGC subsidiary)
ONG-010 | MRPL Power System Upgradation | ONGC | PCR | Grid power system upgrade at MRPL refinery; KPTCL grid linkage for improved power reliability | Karnataka | Mangalore Refinery | KPTCL (Grid linkage) | Ongoing | Apr 2026 | Not Disclosed | 🟢 Commissioned (Apr 2026) | MRPL (ONGC subsidiary)
ONG-011 | MRPL Bio-ATF (Sustainable Aviation Fuel) Demo | ONGC | PCR | Demonstration plant for Bio-ATF / Sustainable Aviation Fuel production at MRPL; green aviation fuel initiative | Karnataka | Mangalore Refinery | In-house / EPC | 2024 | Jan 2027 | Not Disclosed | 🟡 Under Construction | MRPL (ONGC subsidiary)
ONG-012 | MRPL New Petrochemical Complex (West Coast) | ONGC | PCR | Large petrochemical complex integrated with MRPL refinery; configuration under study; shifted focus from refinery expansion; EPC not yet appointed | Karnataka | Near Mangalore / MRPL Refinery Site | Not Yet Appointed (Pre-FID) | TBD (Post FID) | 3–5 years after FID (est. ~2029–31) | ₹30,000–40,000 Cr (USD 3.6–4.8 Billion) | 🔵 Upcoming (Pre-FID) | MRPL (ONGC subsidiary)
ONG-013 | Prayagraj Refinery-cum-Petrochem Complex | ONGC | PCR | Greenfield refinery and petrochemical complex at Naini/Bara; ONGC + BPCL JV; part of O2C expansion plan | Uttar Pradesh | Prayagraj (Naini/Bara) | ONGC + BPCL JV (TBD) | TBD | 2028–2030 (Projected) | ₹1,00,000 Cr (O2C plan) | 🔵 Planned (Feasibility Stage) | ONGC (Direct)
ONG-014 | Jamnagar Refinery & Petrochemical Project | ONGC | PCR | Greenfield refinery and petchem complex at Jamnagar; site selection stage; part of ONGC group's 8 MMTPA petchem target by 2030 | Gujarat | Jamnagar | TBD (Site Selection Stage) | TBD | ~2030 | ₹1,50,000 Cr | 🔵 Planned (Site Selection) | ONGC (Direct)