## RIL Projects
Project ID | Project Name | Parent | Project Owner (Subsidiary) | Sector | State | City | Project Status | Project Type | Construction Start Date | Expected Commissioning Date | Scope
RIL-PCR-001 | Dahej Petrochemical & Polyester Value Chain Expansion (3 MMTPA PTA + 1 MMTPA PET) | Reliance Industries Ltd | Reliance Industries Ltd (O2C Business) | PCR | Gujarat | Dahej, Bharuch District | Ongoing | Brownfield Expansion | Aug 2022 (45th AGM announced; engineering underway) | 31-12-2026 (PTA/PET phases); Full chain by 2026-27 | 3 MMTPA PTA + 1 MMTPA PET integrated polyester value chain. Part of ₹75,000 Cr O2C capex. Dahej prefeasibility: ~₹21,200 Cr for PTA/PET/Carbon Fibre/CPVC/utilities at site.
RIL-PCR-002 | Vinyl Chain (PVC/CPVC) Capacity Expansion – 1.5 MMTPA | Reliance Industries Ltd | Reliance Industries Ltd (O2C Business) | PCR | Gujarat & Maharashtra | Dahej (Gujarat), Jamnagar (Gujarat), Nagothane (Raigad, Maharashtra) | Ongoing | Brownfield Expansion | Aug 2022 (45th AGM; Dahej & Jamnagar target by 2026) | FY2026-27 (Commercial production from new PVC/CPVC units) | 1.5 MMTPA PVC/CPVC across 3 sites. Vinyl-chain capacity more than tripling. Part of ₹75,000 Cr O2C capex. Nagothane projected full commissioning 31-12-2028.
RIL-PCR-003 | Carbon Fibre & Advanced Materials Complex – Hazira | Reliance Industries Ltd | Reliance Industries Ltd (O2C / New Materials) | PCR | Gujarat | Hazira, Surat District | Ongoing | Greenfield | 01-01-2024 (Site preparation confirmed) | 31-12-2025 (Phased rollout; Phase 1 ~20,000 MTPA) | India's first large-scale carbon fibre plant (20,000 MTPA Phase 1). Part of ₹75,000 Cr O2C/new materials capex. Further ramp through 2026-27.
RIL-OG-001 | KG-D6 Incremental Gas Development – R-Cluster & Satellite Cluster Additional Wells | Reliance Industries Ltd | RIL–bp JV (KG-DWN-98/3) | Oil & Gas | Andhra Pradesh (Offshore) | KG-D6 Block – Bay of Bengal (Offshore) | Ongoing | Capacity Addition | 2024 (Govt approval for incremental development plan) | 2025-26 onwards (4-5 mmscmd incremental output; first gas date not specified) | 3 additional wells in R-Cluster + 1 in Satellite Cluster. KG-D6 already producing. Incremental 4-5 mmscmd output targeted. Capex not publicly disclosed. MJ Field first gas: 30-06-2023 (achieved).
RIL-UTL-001 | Dhirubhai Ambani Green Energy Giga Complex – Solar Cell & Module Gigafactory (10-20 GW) | Reliance Industries Ltd | Reliance New Energy Ltd | Utilities | Gujarat | Jamnagar | Ongoing | Greenfield | 01-01-2021 (Phase 1 site works commenced) | 01-04-2025 (First 1 GW HJT line live); Full 10-20 GW by 2026 | 10-20 GW annual solar cell & module manufacturing (quartz-to-module). HJT technology (REC-based), 720 Wp modules. Part of ₹75,000 Cr (~US$10 Bn) new energy capex. BIS-certified production underway.
RIL-UTL-002 | Jamnagar Battery Gigafactory – 40 GWh (Scalable to 100 GWh) | Reliance Industries Ltd | Reliance New Energy Ltd | Utilities | Gujarat | Jamnagar | Ongoing | Greenfield | 30-08-2024 (Civil construction confirmed) | 31-12-2026 (Commercial production; 40 GWh Phase 1) | 40 GWh/year integrated battery manufacturing (scalable to 100 GWh). Part of Jamnagar Giga Complex. US$10 Bn new energy investment envelope.
RIL-UTL-003 | Electrolyser Gigafactory – Jamnagar (3 GW/year capacity) | Reliance Industries Ltd | Reliance New Energy Ltd | Utilities | Gujarat | Jamnagar | Ongoing | Greenfield | 30-08-2024 (Work initiated) | 31-12-2026 (3 GW/year scalable capacity) | 3 GW/year electrolyser manufacturing plant within Jamnagar Giga Complex to support green hydrogen production. Part of US$10 Bn new energy capex.
RIL-UTL-004 | Kutch Ultra-Large Solar & Green Hydrogen Project (~550,000 acres) | Reliance Industries Ltd | Reliance New Energy Ltd | Utilities | Gujarat | Kutch District (Multiple Sites) | Ongoing | Greenfield | 01-08-2024 (Transmission & site works active) | 01-01-2026 (Phased power delivery); Full ramp by 2032 | One of world's largest single-site solar projects (~550,000 acres). Feeds green hydrogen chain targeting 3 MMTPA by 2032. Linked to Jamnagar Giga Complex and Kandla export corridor. Capex not separately disclosed.
RIL-UTL-005 | Green Hydrogen & Green Chemicals Complex – Kandla | Reliance Industries Ltd | Reliance New Energy Ltd | Utilities | Gujarat | Kandla, Kutch District | Ongoing | Greenfield | 2024 (Early enabling works & marine infrastructure) | Later this decade (Initial phases); 3 MMTPA H2 eq. by 2032 | 2,000-acre integrated green hydrogen and green chemicals complex (green ammonia, methanol, SAF). Marine/land infrastructure linked to Kutch solar and Jamnagar Giga Complex. Capex not publicly disclosed.
RIL-DC-001 | Chennai MAA10 Data Centre – 20 MW (on 100 MW campus) | Reliance Industries Ltd | Digital Connexion JV (RIL + Brookfield + Digital Realty) | Data Centres | Tamil Nadu | Chennai | Completed | Greenfield | 2023 (Construction commenced) | Jan 2024 (Phase 1 – 20 MW commissioned) | 20 MW Phase 1 on 100 MW campus. Mukesh Ambani confirmed operations at TN Global Investors Meet Jan 2024. Further expansion to 100 MW in subsequent phases. Capex not separately disclosed.
RIL-DC-002 | Mumbai Chandivali Data Centre Campus – ~40 MW | Reliance Industries Ltd | Digital Connexion JV (RIL + Brookfield + Digital Realty) | Data Centres | Maharashtra | Mumbai (Chandivali) | Ongoing | Greenfield | 2023 (Land acquired; development commenced) | Not Disclosed (Mid-decade commissioning targeted) | 40 MW data centre on 2.15-acre land parcel in Chandivali, Mumbai. Part of Digital Connexion JV's India-wide DC investment plan. Capex not disclosed.
RIL-DC-003 | Jamnagar AI Data Centre – Phase 1 (120 MW) | Reliance Industries Ltd | Jio Platforms Ltd | Data Centres | Gujarat | Jamnagar | Ongoing | Greenfield | 19-02-2026 (Construction confirmed underway) | 31-12-2026 (Phase 1 – 120 MW) | AI-native data centre campus. Construction confirmed at India AI Impact Summit 2026. Phase 1: 120 MW. Integrated with Jamnagar Giga Complex green energy infrastructure.
RIL-DC-004 | Visakhapatnam AI-Native Data Centre Campus – 1 GW | Reliance Industries Ltd | Digital Connexion JV (RIL + Brookfield + Digital Realty) | Data Centres | Andhra Pradesh | Visakhapatnam (Vizag) | Upcoming | Greenfield | 2025-26 (MoU signed; planning & early enabling works) | 2030 (Phased; 1 GW by 2030) | 1 GW AI-native DC campus on ~400 acres. MoU with AP Economic Development Board (2025). Investment ~US$11 Bn (~₹98,000 Cr) by 2030. Pre-construction / planning phase.