## Tata Projects
Project ID | Project Name | Parent | Project Owner (Subsidiary) | Sector | State | City | Project Status | Project Type | Construction Start Date | Expected Commissioning Date | Scope
TAT-UTL-001 | TP Solar 4.3 GW Cell & Module Manufacturing Plant | Tata Group | Tata Power Solar Systems Ltd (TP Solar) | Utilities | Tamil Nadu | Tirunelveli | Ongoing | Greenfield | Jul 2022 (MoU with TN Govt; greenfield development commenced) | Sep 2024 (2 GW cell line commercial production); Full 4.3 GW: FY2026 | 4.3 GW solar cell & module manufacturing plant. Module line: Oct 2023. Cell line: 09-09-2024 (2 GW). Full 4.3 GW capacity target FY26. India's largest integrated solar manufacturing facility.
TAT-UTL-002 | Bhivpuri Pumped Hydro Storage Project (1,000 MW) | Tata Group | Tata Power Ltd | Utilities | Maharashtra | Bhivpuri, Raigad District | Ongoing | Greenfield | 29-10-2024 (Board approved ₹5,666 Cr); EPC awarded 20-03-2025 (HCC–Tata Projects JV) | Oct 2026 (Expected COD per Q2 FY25 analyst presentation) | 1,000 MW pumped hydro storage project. Board approval Oct 2024. ₹2,470 Cr civil & hydro-mechanical EPC contract to HCC–Tata Projects JV (Mar 2025). Part of 2,800 MW PSP portfolio with Shirawta.
TAT-UTL-003 | Shirawta Pumped Hydro Storage Project (1,800 MW) | Tata Group | Tata Power Ltd | Utilities | Maharashtra | Shirawta, Pune District | Upcoming | Greenfield | Jul 2026 (Management confirmed: 'work will start next July' – Nov 2025 statement) | ~2031 (5 years from construction start per management guidance) | 1,800 MW pumped hydro storage project. Investment: ₹11,000 Cr. CEO confirmed Jul 2026 start and 5-year completion timeline at Nov 2025 briefing. Part of Tata Power's 2,800 MW PSP portfolio.
TAT-MIN-001 | West Bokaro Coal Mine Expansion – 10 MTPA Coking Coal Washery | Tata Group | Tata Steel Ltd | Mining | Jharkhand | West Bokaro, Ramgarh District | Completed | Brownfield Expansion | ~Nov 2022 (Per Feb 2022 pre-feasibility report: 19-month construction phase post-EC) | Jun-Sep 2024 (Commissioning & handover per PFR schedule) | New 10 MTPA coking coal washery at West Bokaro. Adds to existing 6.5 MTPA capacity. 20-year washery life from commissioning. Pre-feasibility filed with MoEF&CC Feb 2022.
TAT-MIN-002 | Gandhalpada Iron Ore Mine, Odisha (10 MTPA) | Tata Group | Tata Steel Mining Ltd | Mining | Odisha | Gandhalpada, Sundargarh District | Upcoming | Greenfield | Not Disclosed (Mining lease not yet executed; forest diversion approval pending) | FY2029 (Production start per VP Raw Materials statement to PTI) | 10 MTPA iron ore mine (314.37 Mt resources; 33-year mine life). LoI for 50-year lease over 241.1 ha issued 28-10-2021. Forest clearance (216.875 ha) applied. Production target FY29 to replace expiring leases.
TAT-MIN-003 | Noamundi / Joda / Katamati Iron Ore Mine Expansion (40 → 55 MTPA) | Tata Group | Tata Steel Ltd (OMQ Division) | Mining | Odisha & Jharkhand | Noamundi (JH), Joda & Katamati (OD) | Ongoing | Expansion | FY2025 (Phased expansion programme announced Apr-May 2025; works underway) | FY2030 (55 MTPA full run-rate over 5 years from 2025) | Multi-site iron ore capacity expansion from 40 MTPA to 55 MTPA across OMQ division. Investment: ~₹10,000 Cr (~US$1.18 Bn). Technology, logistics and debottlenecking upgrades. No single commissioning date – phased ramp-up.
TAT-DC-001 | Tata Group 1 GW AI Data Centre Programme (TCS HyperVault + OpenAI + AMD) | Tata Group | TCS / Tata Communications | Data Centres | Multiple States (TBD) | Multiple Sites (TBD) | Upcoming | Greenfield | Not Disclosed (Announced at India AI Impact Summit 2026; no groundbreaking date published) | Not Disclosed (Phased: 100 MW initial phase, scaling to 1 GW; timeline not published) | 1 GW AI-optimised data centre programme. Phase 1: 100 MW via TCS HyperVault. Partnerships: OpenAI, AMD, TPG. Total capex: ~US$6.5-7 Bn. Announced Feb 2026. Construction timelines and site locations not yet disclosed.